## Sheet1
Step | Activity |  | Status
1 | Create project directory(Git Hub) | Create the main folder to store all project files, code, and documentation. | Completed
2 | Initialize Git | Run git init to enable version control and track changes to project files. | In Progress
3 | Open project in VS Code | Open the project folder in VS Code for development and file management. | Pending
4 | Create folder structure | Organize the project into folders such as backend, frontend, docs, tests, and data. | Pending
5 | Initial SDD Setup | Define the project vision, business problem, scope, high-level requirements, constraints, and expected outcomes before development. | Pending
6 | Create root-level AGENTS.md | Define common coding standards, security rules, and development guidelines for Codex across the entire repository. | Pending
7 | Create folder-level AGENTS.md files | Define folder-specific instructions for backend development, statistical analysis, frontend development, testing, data management, and documentation. | Pending
8 | Create reusable SKILL.md files | Create reusable workflows that guide Codex through specific tasks, such as statistical analysis, data validation, and code review. | Pending
9 | Prepare BRD and specifications | Document the business problem, functional requirements, non-functional requirements, user stories, and acceptance criteria. | Pending
10 | Design application architecture | Define how the frontend, backend, OpenAI API, database, and statistical analysis engine will communicate. | Pending
11 | Start implementation using Codex | Use Codex to develop the application based on approved specifications, coding standards, and architecture. | Pending
12 | Testing, CI/CD and deployment | Perform unit, integration, statistical, and security testing; automate validation using CI/CD; and deploy to a test environment. | Pending
13 | Push project to GitHub | Commit and push project files to GitHub to maintain version history and enable team collaboration. | Pending
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Without SDD (Vibe Coding): You tell Codex: Create an AI application to analyze trade promotions. Codex starts generating code, but the requirements may not be clear. With SDD: We follow a structured process: Specify: Define what the application should do. Plan: Decide the architecture, technologies, and implementation approach. Tasks: Break the requirements into smaller development tasks. Implement: Use Codex to write code based on the specifications. Validate: Test whether the application meets the acceptance criteria.